SAMPLE Production Schedule (Narrative Format)

This is a sample production schedule showing the dates and periods for each major stage of production.

This has been done in a narrative format, but could also be done in a calendar format.

|  | Stage |  |  | From |  |  | To (times ) |  | Period | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Pre-production |  | Monday 5 January |  | Friday 23 January |  | 2 weeks |  |  |
|  | Location recce | Tuesday 13 January | 0830 – 1230 |  | 4 hours | All key crew booked |
|  | Shoot |  | Monday 19 January |  | Friday 23 January |  | 5 days |  |  |
|  | Edit |  | Monday 19 January |  | Friday 6 February |  | 3 weeks | Edit asst. required nights during shoot week |
|  | Rough cut screening | Monday 2 February |  |  |  | – |  |  |
|  | Investors’ screening | Wednesday 4 February |  |  |  | – |  |  |
|  | Compile |  | Friday 6 February |  |  |  |  | 6–8 hours | Edit asst. required night Thur 5 & all day Fri 6 |
|  | Grade |  | Tuesday 10 February |  | 0900 – 1400 |  | 4–5 hours | booked |
|  | Online |  | Tuesday 10 February |  | 1600 – 2000 |  | 3–4 hours | booked |
|  | Master tech check | Thursday 12 February |  | tbc |  | 2 hours | to be confirmed |
|  | Tracklay/foley | Saturday 7 February | Tuesday 10 February | 4 days | booked |
|  | Mix |  | Wednesday 11 February | 0900 – 1700 | 8 hours | booked |
|  | Dubs/tech checks | Thursday 12 February |  |  |  |  |  |  | Facility yet to be confirmed & booked |

Master/delivery	Friday 13 February	PA to assist with deliverable